## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Data Science Project Development |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | Ram Vishal Gobind |  |  |  |  | DATE | [6 empty] | 2018-03-12
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Literature Review
1.1 | Finalise Research Topic (Determine the problem) | Vishal R | 2020-10-26 | 2020-11-03 | 7 | 70% | bar: WEEK 1 T to WEEK 2 T
1.1.1 | Research of data sets available | Vishal R | 2020-10-26 | 2020-11-07 | 11 | 0% | bar: WEEK 2 W
1.2 | Literature review of 15 Academic Journals | Vishal R | 2020-10-26 | 2020-11-10 | 14 | 0% | bar: WEEK 2 W to WEEK 3 W
1.3 |  | Vishal R |  |  |  | 40% | bar: WEEK 2 R to WEEK 3 R
1.4 |  | Vishal R |  |  |  | 70% | bar: WEEK 3 M to WEEK 3 R
1.5 |  | Vishal R |  |  |  | 60% | bar: WEEK 3 T to WEEK 3 R
1.6 |  | Vishal R |  |  |  | 50% | bar: WEEK 3 F
2 | Product Prototype
2.1 |  | Vishal R |  |  |  | 22% | bar: WEEK 4 M to WEEK 4 R
2.2 |  | Vishal R |  |  |  | 16% | bar: WEEK 4 F to WEEK 5 F
2.3 |  | Vishal R |  |  | 0 | 0%
2.4 |  | Vishal R |  |  | 0 | 0%
3 | Project Report
3.1 |  | Vishal R |  |  | 0 | 0%
3.2 |  | Vishal R |  |  | 0 | 0%
3.2.1 |  | Vishal R |  |  | 0 | 0%
3.2.2 |  | Vishal R |  |  | 0 | 0%
3.3 |  | Vishal R |  |  | 0 | 0%
3.3.1 |  | Vishal R |  |  | 0 | 0%
4 | Result Deliverables
4.1 |  | Vishal R |  |  | 0 | 0%
4.2 |  | Vishal R |  |  | 0 | 0%
4.3 |  | Vishal R |  |  | 0 | 0%
4.4 |  | Vishal R |  |  | 0 | 0%